## Sheet1
Date | Actual Time Remaining | Estimated Work Remaining | Total hours: | 800 | Instructions:
2025-08-08 | 240 | 240 |  |  | • Replace the dates with the dates for your project. You may also replace these with arbitary time steps (such as Week 1, Week 2, etc)
2025-08-15 | 224 | 217 |  |  | • Replace the Total Hours to the amount of hours you have calculated you will need to work to achieve all your tasks. The Estimated Work Remaining values will automatically adjust.
2025-08-22 | 208 | 193 |  |  | • While working through your project, update the Actual Work Remaining column with your actual progress in burning down your work, and keep track of your performance versus your projected performance.
2025-08-29 | 192 | 180
2025-09-05 | 176 | 170
2025-09-12 | 160 | 155
2025-09-19 | 144 | 143
2025-09-26 | 128 | 120
2025-10-03 | 112 | 96
2025-10-10 | 96
2025-10-17 | 80
2025-10-24 | 64
2025-10-31 | 48
2025-11-07 | 32
2025-11-14 | 16
2025-11-21 | 0