## Sheet 1
Table 1
Weeks | Max | Brodie | Eddison
2025-08-08 | Tutorial level | Character move & turn
2025-08-15 | Menu | Character move advanced | Level prefabs
22/8/2025 : Alpha build complete | Menu & tutorial update | Character turn fixes
2025-08-29 | Menu | Enemy physics & win cond’ fix movement bugs: DONE | Pin model & texture
2025-09-05 | Menu & tutorial update | Fix move script bugs and implement new pin | Bowling ball roller
2025-09-12 | Update tutorial level | Update work files | Bowling ball roller animations
2025-09-19 | Level 4 | Movement | That one sign
2025-09-26 | Level 2 and timer | Fixing movement | Bowling ball finish
2025-10-03 | Level 2/3 and timer | Fixing bowling ball finish and basically entire game. | Testing
2025-10-10 | Level 3/5 | Fixing movement | Documentation
2025-10-17 | Level 6 | Best time saving | Music
2025-10-24 | Showing best time more places | Actually making best time saving | Sound effects
2025-10-31 | UI fixes | Documentation | Music
2025-11-07 | Documentation & professional clash gaming | Fixing movement | Music
2025-11-14 | Game finished | Game finished | Game finished
2025-11-21 | Documentation | Documentation | Documentation