## Sheet1
Date | Actual Work Remaining | Estimated Work Remaining | Total hours: | 800 | Instructions:
2017-03-21 | 800 | 800 |  |  | • Replace the dates with the dates for your project. You may also replace these with arbitary time steps (such as Week 1, Week 2, etc)
2017-03-22 | 780 | 782 |  |  | • Replace the Total Hours to the amount of hours you have calculated you will need to work to achieve all your tasks. The Estimated Work Remaining values will automatically adjust.
2017-03-23 | 750 | 764 |  |  | • While working through your project, update the Actual Work Remaining column with your actual progress in burning down your work, and keep track of your performance versus your projected performance.
2017-03-24 | 740 | 745
2017-03-25 | 730 | 727
2017-03-26 | 720 | 709
2017-03-27 | 710 | 691
2017-03-28 | 700 | 673
2017-03-29 | 690 | 655
2017-03-30 | 660 | 636
2017-03-31 | 640 | 618
2017-04-01 | 630 | 600
2017-04-02 | 610 | 582
2017-04-03 | 550 | 564
2017-04-04 | 510 | 545
2017-04-05 | 480 | 527
2017-04-06 | 440 | 509
2017-04-07 | 420 | 491
2017-04-08 | 401 | 473
2017-04-09 | 390 | 455
2017-04-10 | 380 | 436
2017-04-11 | 370 | 418
2017-04-12 | 360 | 400
2017-04-13 | 330 | 382
2017-04-14 | 300 | 364
2017-04-15 | 250 | 345
2017-04-16 | 200 | 327
2017-04-17 | 180 | 309
2017-04-18 | 160 | 291
2017-04-19 | 140 | 273
2017-04-20 | 100 | 255
2017-04-21 | 50 | 236
2017-04-22 | 40 | 218
2017-04-23 | 20 | 200
2017-04-24 | 0 | 182
2017-04-25 |  | 164
2017-04-26 |  | 145
2017-04-27 |  | 127
2017-04-28 |  | 109
2017-04-29 |  | 91
2017-04-30 |  | 73
2017-05-01 |  | 55
2017-05-02 |  | 36
2017-05-03 |  | 18
2017-05-04 |  | 0