## Sheet 1
Table 1
Weeks | Max | Brodie | Eddison
2025-08-08 | Tutorial level | Character move & turn
2025-08-15 | Menu | Character move advanced | Level prefabs
22/8/2025 : Alpha build complete | Menu & tutorial update | Character turn fixes
2025-08-29 | Menu | Enemy physics & win cond’ fix movement bugs: DONE | Pin model & texture
2025-09-05 | Menu & tutorial update | Fix move script bugs and implement new pin | Bowling ball roller
2025-09-12 | Update tutorial level | Update work files | Bowling ball roller animations
2025-09-19
2025-09-26
2025-10-03
2025-10-10
2025-10-17
2025-10-24
2025-10-31
2025-11-07
2025-11-14
2025-11-21